Data Study Group of the

IHBG Formula Negotiated Rulemaking Committee

Proposed Framework for Data Study Group Meetings and Process

Step One:

Establish and adopt this Framework for Data Study Group Meetings and Process

Adopt document providing an overview of the Study Group’s Data Source Assessment process (see the document presently titled “Overview of Evaluation”)

Establish an outline for the format of the Final Report

Establish process and timeline for nominating data sources for evaluation (including proposed nomination form)

Step Two:

Approve tools to be used to screen,and evaluate nominated data sources (see Data Source Characterization and Evaluation Process Matrices)

Step Three:

Compile and finalize list of data sources submitted by Data Study Group members and participants and by others in response to the Federal Register notice

Identify technical support person(s) who will screen and evaluate nominated data sources

Assign list of nominated data sources to technical support person(s) for screening

Step Four (no more than one month after closing of nomination period):

Data source screening complete

Discussion to narrow down list of data sources to evaluate based on screening

List and discuss current variables

Identify technical support person(s) to evaluate data sources (if different than those identified for data source screening)

Assign data sources meeting minimum qualifications to technical support person(s) for full evaluation (preliminary evaluation due four weeks after assignment)

Step Five (no more than one month after screening phase):

Discuss preliminary evaluation of data sources

Identify, draft and submit additional questions and/or requests for information to HUD or other relevant agencies to facilitate full evaluation of sources

Step Six (no more than one month after submission of preliminary evaluation):

Conference Call: Review and discuss responses to questions and requests for information, and address any unresolved questions or requests

Step Seven (no more than one month after previous meeting to finalize data source evaluation report):

Consider report containing evaluation of data sources (including assessment of suitability for measuring current variables)

Determine final list of data sources, and the variables they measure, for consideration by the Data Study Group

Select optimal data source(s) to measure current variables based on overall evaluation criteria

- If applicable, identify potential means to improve or enhance the data provided by these source(s), identifying the resources needed to implement such improvements and weighing the costs of those improvements against their potential value.

Identify other potential variables (not presently included in the IHBG formula) that could be measured using data from the sources that have been evaluated.

Technical support person(s) to prepare draft report containing recommendations for Committee no later than May 28, 2015.

Steps Eight and Nine

Review draft recommendations report prior to submission to Negotiated Rulemaking Committee (draft provided to Study Group at least two weeks prior to review)

Discuss revisions to draft and finalize report language, including minority and majority opinions if consensus cannot be reached

Submit final report language to Negotiated Rulemaking Committee no later than July 28, 2015.

# Comments

Is there a reason to replace the term “characterize” with the term “screen”?  If so, we should update the title of the data characterization process matrix and make corresponding revisions to the evaluation process overview document.

Why eliminate the language about closing the data source nomination period?

Moved from Step Two

Information about the variables that each relevant, reliable data source can measure should be reported back to the Full Committee, and we have suggested a process for that.  See the Assessment Process overview document and Step 7 below.  However, the variables that a source could potentially measure should not cause it to score higher in the evaluation process.  The Committee has not provided directive on what the “right” variables are, and it is not appropriate for the Study Group to prioritize one data source over another based upon its ability to measure variables that are not presently in the formula.