## Timeline
Denotes an in-person Study Group Meeting
Denotes a telephonic Study Group Meeting
Denotes Technical Expert Meeting
Denotes where we currently are in the process
Stage | Duration | Date | Day of the Week | Activity | Date Completed | Notes
Meeting |  | 12/1-12/2 | Mon/Tues | STUDY GROUP IN-PERSON MEETING
Assessment & Process Documents |  | 2014-12-05 | Fri | Send final draft assessment documents to study group members for final review | 2014-12-04
| 2 days | 2014-12-09 | Tues | Study group members send final approval to HUD on assessment & process documents | 2014-12-17 | 3 SG members did not explicitly send any feedback or approval. Given the length of time since the due date, HUD decided to finalize documents and post them to the website.
| 1 day | 2014-12-10 | Wed | HUD uploads documents to IHBG website; nomination phase commences | 2014-12-17
Meeting |  | 2014-12-17 | Wed | STUDY GROUP TELEPHONE MEETING
Nomination Phase (3 weeks) | 3 weeks | 2014-01-07 | Wed | Nomination of sources and designation of experts are due. Screening process commences. Note, if a study group member can't find an expert during this period, the expert can start at any time during the evaluation process
Meeting |  | 2014-01-12 | Mon | STUDY GROUP TELEPHONE MEETING
Screening Phase (3 weeks) |  | 2015-01-23 |  | Technical experts meet over the phone to discuss screening results | 2015-01-23
| 2 weeks | 2014-01-21 | Wed | Experts finish first draft of screening; sends draft to study group members | 2015-01-25 | Ben W. sent email to Study Group with results of screening process, including summary to help discussion
|  | 2015-01-26 | Mon | STUDY GROUP TELEPHONE MEETING
| 1 week | 2014-01-28 | Wed | Study group finalizes screening; characterization phase commences | 2015-01-26 | Study group met on 1/26 and reviewed technical experts' screening recommendations. Members agreed to move 17 / 43 nominations to the characterization phase.
Characterization Phase (11 weeks) |  | 2015-01-27 |  | Technical experts meet over the phone to divvy up 17 nominations for initial review. | 2015-01-27
|  | 2015-02-11 | Wed | 1st round of draft characterizations are completed; experts rotate drafts
| 2 weeks | 2015-02-10 | Tues | Technical experts discuss among themselves first round of initial characterizations.
| 3 weeks | 2014-03-04 | Wed | All experts finalize draft characterizations and ciruclate drafts to study group members | 2015-04-17
|  | 2015-03-02 | Mon | STUDY GROUP MEETING
Note: Technical met multiple times during the characterization phase, which are not recorded here
|  | 2015-03-16 | Mon | STUDY GROUP MEETING - Decisions on 1st round of characterizations
|  | 2015-04-20 | Mon | STUDY GROUP MEETING - Final Deceisions on 2nd round of characterizations
Evaluation Phase (6 weeks) |  | 2015-04-27 | Mon | STUDY GROUP MEETING - Discuss Final Report Outline
| 4 weeks | 2015-05-18 | Mon | All experts finalize draft evaluations and circulates drafts to study group members
|  | 2015-05-26 | Tues | STUDY GROUP MEETING - 1st Discussion on Evaluation Drafts
|  | 2015-06-01 | Mon | STUDY GROUP MEETING - 2nd Discussion on Evaluation Drafts
Final Report Phase (8 weeks) | ~3 weeks | 2015-06-19 | Fri | DRAFT final report sent to study group
|  | 6/23 - 6/24 | Mon | STUDY GROUP MEETING - Discuss Final Report Draft
| 5 weeks | 2014-07-28 | Tues | Final Report due to full committee