## Timeline
Stage | Duration | Date | Day of the Week | Activity | Date Completed | Notes
Meeting |  | 12/1-12/2 | Mon/Tues | STUDY GROUP IN-PERSON MEETING
Assessment & Process Documents |  | 2014-12-05 | Fri | Send final draft assessment documents to study group members for final review | 2014-12-04
| 2 days | 2014-12-09 | Tues | Study group members send final approval to HUD on assessment & process documents | 2014-12-17 | 3 SG members did not explicitly send any feedback or approval. Given the length of time since the due date, HUD decided to finalize documents and post them to the website.
| 1 day | 2014-12-10 | Wed | HUD uploads documents to IHBG website; nomination phase commences | 2014-12-17
Meeting |  | 2014-12-17 | Wed | STUDY GROUP TELEPHONE MEETING
Nomination Phase (3 weeks) | 3 weeks | 2014-01-07 | Wed | Nomination of sources and designation of experts are due. Screening process commences. Note, if a study group member can't find an expert during this period, the expert can start at any time during the evaluation process
Meeting |  | 2014-01-12 | Mon | STUDY GROUP TELEPHONE MEETING
Screening Phase (3 weeks) | 2 weeks | 2014-01-21 | Wed | Experts finish first draft of screening; sends draft to study group members
| 1 week | 2014-01-28 | Wed | Study group finalizes screening; characterization phase commences
Characterization Phase (7 weeks) | 2 weeks | 2014-02-11 | Wed | 1st round of draft characterizations are completed; experts rotate drafts
| 3 weeks | 2014-03-04 | Wed | All experts finalize draft characterizations and ciruclate drafts to study group members
| 2 weeks | 2014-03-18 | Wed | Study group members give written feedback to experts; study group decides which data sources do not move to evaluation phase; evaluation phase commences
Evaluation Phase (7 weeks) | 2 weeks | 2014-04-01 | Wed | 1st round of evaluations are completed; experts rotate drafts
| 3 weeks | 2014-04-22 | Wed | All experts finalize draft evaluations and circulates drafts to study group members
| 2 weeks | 2014-05-06 | Wed | Study group meets and discusses evaluations, sends experts written feedback; experts commence full report
Final Report Phase (12 weeks) | 4 weeks | 2014-06-03 | Fri | DRAFT final report sent to study group
| ~8 weeks | 2014-07-28 | Tues | Final Report due to full committee

## Changes to timeline
No. | Date of Change | Change | Effect of Change
1 | 2014-12-17 | We were one week late uploading finalized process documents and others wanted the nomination process to be extended | All items shift out 1 week; review period for draft final report is squeezed a few days.
2
3
4
5
6